## Sheet1
1 | 1

## Sheet2
[7 empty] | Harrop Pr | Home BC 4.26 | Paper 0.80
Expenses Already Paid or Billed |  | 41757.32 | 41757.32 |  |  | sq ft | 2.65 + .50
| Status | High Estimate | Low Estimate | Paid so far | Main Sh Rm | 930 | 2929.5 | 3961.8 | 744
Architect | partly paid |  |  |  | comm rm + Fam Rm | 810 | 2551.5 | 3450.6 | 648
Engineer |  |  |  |  | Hallway | 216 | 680.4 | 920.16 | 216
Asbestos | done |  |  |  | Tenno + back Sh rm | 470 | 1480.5 | 2002.2 | 376
building permit | done |  |  |  | Totals | 2426 | 7641.9 | 10334.76 | 1984
trusses | done
electrical |  | 3000 | 3000 |  | Main Shrine @4.26, hallway rest HP |  |  | 8674.2
Insulate shed roof |  | 954 |  |  | Main Shrine @4.26, comm rm & Fam rm HP, rest paper |  |  | 7105.3
Spray foam in crawl space box ends |  | 882 |  |  | Main Shrine Rm & com Rm &Fam rm HP, rest paper |  |  | 6073
attic insulation |  | 3137 | 1900 |  | All exept entry, kitchen &bathrooms @4.26 maple |  |  | 10335
sound insulate family room wall |  | 712 |  |  | All exept entry, kitchen &bathrooms @3.15 finished H. P. |  |  | 7642
HVAC |  | 4000 | 4000 |  | All exept entry, kitchen &bathrooms @0.80 paper |  |  | 1984
plumbing |  | 3000 | 3000
Finish Carpentry
drywall, materials and labor, (subcontract) |  | 19000 | 17033
Miscelaneous supplies, home building centre |  | 3017 | 3017 |  | Kitchen | 99
Doors
windows
flooring kitchen and entry
flooring: wood, in main shrine room, com. Rm. and Family room |  | 5500 | 8000
flooring, hallway
kitchen cabinets |  | 7000 | 4160
Siding, Hardie board materials only, unpainted, tax included, price is volume dependent |  | 4600 | 3924
Skylights
Utilities
Sign
Replace roof on back shed |  | 4200 | 4200
Paint (Materials only) |  | 1170 | 1170
Scaffold rentil til March 31 |  | 524 | 524
Labor Jan 1 -Feb 28 or March 31 |  | 30556 | 16747 | 3604
Totals |  | 133009.32 | 108508.32
Note on C2: Rodgers Russell: This includes everything that has been labeled "done".
Note on C9: Rodgers Russell: Kootenay Lake electric
Note on C10: Rodgers Russell: Brian Garvin, tax not included. Doesn’t include west wall. Drywall covering?
Note on C11: Rodgers Russell: Brian Garvin, tax not included.
Note on C12: Rodgers Russell: Sander's
Note on C13: Rodgers Russell: Brian Garvin, high density blown cellulose.
Note on C17: Rodgers Russell: Brian, quality Int Contr. Includes GST and materials
Note on D17: Rodgers Russell: Sander's estimate
Note on C18: Rodgers Russell: Bill to Jan 22
Note on D18: Rodgers Russell: Bill to Jan 22
Note on C22: Rodgers Russell: Wood floors from Harrop Proctor, no labor included, just doing the main shrine room, community and family room.
Note on D22: Rodgers Russell: All spaces done with wood floors from harrop-Proctor except for entry and kitchen.
Note on C24: Rodgers Russell: Sander's estimate
Note on D24: Rodgers Russell: Rodgers Russell: This estimate is from Ikea. It includes a laminate counter top, but does not include shipping or the sink. It does not include handles or the base board. Note: the laminate countertop may not match the top on the island.
Note on C25: Rodgers Russell: plank siding for whole building. (Shingles would be $9600), tax included
Note on D25: Rodgers Russell: Sheet siding, based on price for 4'x9' sheets, includes tax
Note on C29: Rodgers Russell: Neil's estimate, torch down
Note on C32: Rodgers Russell: Rodgers Russell: This is based on two carpenters @27/hr and a helper at 20/hr. For the month of January Dale is likely to work one day per week. This estimate assumes that we stop at the the end of March
Note on D32: Rodgers Russell: This is based on two carpenters @27/hr and a helper at 20/hr. For the month of January Dale is likely to work one day per week. This estimate assumes that we stop at the end of Feb.
Note on G32: Rodgers Russell: This is based on two carpenters @27/hr and a helper at 20/hr. For the month of January Dale is likely to work one day per week. This estimate assumes that we stop at the end of Feb.